## Synthèse
Action Plan to Digitalise DASUR Processes
| Percentage work_flow |  | 20% | 2024-05-31
SN | Actions | Days | Progression
1 | Point of agreement | 1 | 100%
2 | Analyse , conception et implémentation | 56 | 0%
#REF! | #REF! | #REF! | #REF!
4 | UATs Validation | 6 | 0%
5 | Production Stage | 6 | 0%

## Système de Reporting CallCenter
Action Plan to Digitalise DASUR Processes
|  | 69 |  |  | Percentage work_flow |  |  |  | 20%
SN | Actions | Days |  | Status | Output | Needs | Start_date | End_date | Progression | Deadline | Dept
1 | Point of agreement | 1 | [6 empty] | 100%
1.1 | Meeting_report | 1 | DASI | Completed | Information by Mail |  | 2023-11-04 | 2023-11-04 | 100% |  | IT
2 | Analyse , conception et implémentation | 56 | [6 empty] | 0%
2.1 | Analyse | 9 | DASI | Not yet started | Functional Documentation | Endevour to be in a calm zone for work to take place | 2023-12-20 | 2023-12-28 | 0% |  | IT
2.2 | Conception | 13 | DASI | Not yet started | Technical Documentation |  | 2023-12-29 | 2024-01-10 | 0% |  | IT
2.3 | Implementation | 31 | DASI | Not yet started |  |  | 2024-01-11 | 2024-02-10 | 0% |  | IT
2.4 | Providing_User_Guide | 3 | DASI | Not yet started | User_Guide |  | 2024-02-11 | 2024-02-13 | 0% |  | IT
4 | UATs Validation | 6 | [6 empty] | 0%
4.1 | Data quality controle | 4 | DASUR | Not yet started | Test report and recommandation |  | 2024-02-15 | 2024-02-18 | 0% |  | IT
4.2 | UATs Validation | 2 | DASUR | Not yet started | UAT doc |  | 2024-02-19 | 2024-02-20 | 0% |  | IT
5 | Production Stage | 6 | [6 empty] | 0%
5.0 | Demande for RFC Replacement | 2 | DASI | Not yet started | RFC |  | 2024-02-20 | 2024-02-22 | 0% |  | IT
5.1 | Internal Comunication | 1 | DASUR / DASI | Not yet started | ENEO News Publication |  | 2024-02-23 | 2024-02-23 | 0% |  | IT
5.2 | Put New Version into Production | 2 | DASI | Not yet started | Information Mail |  | 2024-02-24 | 2024-02-25 | 0% |  | IT
5.3 | Post migration Review meeting | 1 | IT/DAAM | Not yet started | migration closing email |  | 2024-02-26 | 2024-02-26 | 0% |  | IT
6 | Support Reporting for DASUR Processes |  | ENEO
| Not yet started | 0%
| In progress | 1%
| Completed | 2%
3%
4%
| Gildas | 5%
| Marcel Cedric | 6%
| Jacques Armand | 7%
| Karl Nyabe | 8%
| Herve Ngando | 9%
| Digital Applications Team | 10%
| Direction Adjointe Analyses Et Marketing | 12%
| DASI | 13%
| DAAM | 0%
IT/DAAM
ENEO/LMT
| LMT | 0%
| ENEO | 14%
0%
15%
16%
17%
18%
19%
20%
21%
22%
| DAAM | 23%
| IT | 24%
| DFI | 25%
| EMEX | 26%
| IT/DHSE | 27%
| DHSE | 28%
| IT/DAAM | 29%
30%
31%
32%
33%
34%
35%
36%
37%
38%
39%
40%
41%
42%
43%
44%
45%
46%
47%
48%
49%
50%
51%
52%
53%
54%
55%
56%
57%
58%
59%
60%
61%
62%
63%
64%
65%
66%
67%
68%
69%
70%
71%
72%
73%
74%
75%
76%
77%
78%
79%
80%
81%
82%
83%
84%
85%
86%
87%
88%
89%
90%
91%
92%
93%
94%
95%
96%
97%
98%
99%
100%
Formulas:
Start_date = [End_date, row above]+1
End_date = [Start_date]+30
End_date = [Start_date]

## Incidents
N° | Date | Description de l'incident | Severité (1-->4) | Cause | Action | Responsable
1 |  |  | 1
2 |  |  | 1
3 |  |  | 2
4 |  |  | 3
5 |  |  | 4

## Rollback planning
| Dates |  | Acteurs
| Début | Fin
Constat de l'echec |  |  | IT/DAAM
Information DBA & NOC |  |  | Digital applications
Test sécurité |  |  | IRM
Test techniques applicatif |  |  | Digital applications
Test fonctionnel du système |  |  | Call Center
communication aux divers utilisateurs |  |  | Jacques Armand , Hervé Ngando
Mise en production et mise à jour eneoportal |  |  | IT Automation
Review meeting post roolback |  |  | IT & Call center Team