## Synthese
Action Plan of testing ICN cashing Application
| Percentage | 0% | 2024-09-02
SN | Actions | Progression
1 | Point of agreement | 0%
2 | Preparing the Testing infrastructure | 0%
3 | Testing: Unit Test | 0%
4 | Testing: Integration testing | 0%
5 | Testing: End-to-End (E2E) | 0%
6 | Testing: Security Testing | 0%
7 | Performance Testing | 0%
8 | User Acceptance Test (UAT) | 0%

## Action Plan
Action Plan of testing ICN cashing Application
|  |  |  | Percentage |  | 0%
SN | Actions | Owner | Status | Output | Needs | Progression
1 | Point of agreement |  |  |  |  | 0%
1.1 | Scoping meeting with Testing Team | Testing Team | Not yet started | Information by Mail |  | 0%
2 | Preparing the Testing infrastructure |  |  |  |  | 0%
2.0 | Providing Test server | Ibrahim | Not yet started |  |  | 0%
2.1 | Deploying a Mongo database | Emmanuel | Not yet started |  |  | 0%
2.2 | Deploying a Next.js Application with Nginx and PM2 | Development Team | Not yet started |  |  | 0%
2.2.1 | Step 1: Install Node.js and npm | Development Team | Not yet started |  |  | 0%
2.2.2 | Step 2: Install PM2 | Development Team | Not yet started |  |  | 0%
2.2.3 | Step 3: Clone Your Next.js Application | Development Team | Not yet started |  |  | 0%
2.2.4 | Step 4: Install Dependencies | Development Team | Not yet started |  |  | 0%
2.2.5 | Step 5: Build Your Next.js Application | Development Team | Not yet started |  |  | 0%
2.2.6 | Step 6: Start Your Application with PM2 | Development Team | Not yet started |  |  | 0%
2.2.7 | Step 7: Install and Configure Nginx | Development Team | Not yet started |  |  | 0%
2.2.8 | Step 8: Access Your Application | Development Team | Not yet started |  |  | 0%
2.2.9 | Step 9: Monitor Your Application | Development Team | Not yet started |  |  | 0%
3 | Testing: Unit Test |  |  |  |  | 0%
3.1 | Step 1: Design Unit test cases, test scenarios. | Testing Team | Not yet started |  |  | 0%
3.2 | Step 2: Setting Up the Test Tools . | Testing Team | Not yet started |  |  | 0%
3.3 | Step 3: Writing a Unit Test | Testing Team | Not yet started |  |  | 0%
3.4 | Step 4: Running the Tests | Testing Team | Not yet started | Unit Test Report |  | 0%
4 | Testing: Integration testing |  |  |  |  | 0%
4.1 | Step 1: Prepare the test plan. | Testing Team | Not yet started |  |  | 0%
4.2 | Step 2: Design test cases, test scenarios, use cases and scripts. | Testing Team | Not yet started |  |  | 0%
4.3 | Step 3: Run tests after unit/module integration. | Testing Team | Not yet started |  |  | 0%
4.4 | Step 4: Detect, report and fix errors | Testing Team | Not yet started | Integration Test Report |  | 0%
4.5 | Repeat the process until all bugs are found and fixed. | Testing Team | Not yet started |  |  | 0%
5 | Testing: End-to-End (E2E) |  |  |  |  | 0%
5.1 | List the input and output data for each system | Testing Team | Not yet started |  |  | 0%
5.2 | List the input and output data for each system | Testing Team | Not yet started |  |  | 0%
5.3 | Step 4: Detect, report and fix errors | Testing Team | Not yet started | Integration Test Report |  | 0%
6 | Testing: Security Testing |  |  |  |  | 0%
6.1 | Listing of common knowledge of vunerablity | Franck Nsimi | Not yet started |  |  | 0%
6.2 | Step 2: Perform security test, Detect, report. | Franck Nsimi | Not yet started | Security test report |  | 0%
7 | Performance Testing |  |  |  |  | 0%
7.1 | Identify Performance Metrics. | Testing Team | Not yet started |  |  | 0%
7.2 | Design and write script to simulate overload | Testing Team | Not yet started |  |  | 0%
7.3 | Execute performance Tests. | Testing Team | Not yet started |  |  | 0%
7.4 | Analyze, Report, Retest | Testing Team | Not yet started |  |  | 0%
7.5 | QA/Testing Environment | Testing Team | Not yet started |  |  | 0%
8 | User Acceptance Test (UAT) |  |  |  |  | 0%
8.1 | Perform Test | Parfait Tsegue | Not yet started |  |  | 0%
8.2 | UAT Report | Parfait Tsegue | Not yet started | UAT Report |  | 0%
Not yet started
In progress
Completed
Gildas
Ferdinand Charles / Jacques Armand / Herve Ngando
Jacques Armand
Karl Nyabe
Herve Ngando
Ferdinand Charles
Emmanuel
Ibrahim
Direction Adjointe Analyses Et Marketing
DASI
DAAM
IT/DAAM
ENEO/LMT
LMT
ENEO
INFASME
DAAM
IT
DFI
EMEX
IT/DHSE
DHSE
IT/DAAM

## Incidents
N° | Date | Incident description | Severite (1-->4) | Cause | Action | Owner
1 |  |  | 1
2 |  |  | 1
3 |  |  | 2
4 |  |  | 3
5 |  |  | 4

## Rollback planning
| Dates |  | Owner
| Start | End
Constat de l'echec
Information DBA & NOC |  |  | Digital applications
Test sécurité |  |  | IRM
Test techniques applicatif |  |  | Eugene Ekoule , Jacques Armand , Hervé Ngando
Test fonctionnel du système |  |  | Parfait Tsegue
communication aux divers utilisateurs |  |  | Eugene Ekoule , Jacques Armand , Hervé Ngando
Mise en production et mise à jour eneoportal |  |  | IT Automation
Review meeting post roolback |  |  | IT & Development team & Testing team